## Sheet1
Process # | ACTION | TARGET DATE | ESTIMATED COST | COMPLETED (Y/N) | PHASE
1 | Purchase property | 2025-10-03 | 2500 | N | Property/Shed
2 | Confirm 911 address | 2025-10-06 | 0 | N | Property/Shed
3 | Move 12×32 shed onto gravel/pier base | 2025-11-01 | 700 | N | Property/Shed
4 | Connect electric (meter, subpanel, grounding) | 2025-11-01 | 2000 | N | Property/Shed
5 | Connect water (tie into existing line, shutoff, insulation) | 2025-11-30 | 1500 | N | Property/Shed
6 | Work with septic installer (soil test, design, permit) | 2025-12-31 | 7000 | N | Property/Shed
7 | Make shed livable with basics (insulation, HVAC, kitchenette, security) | 2025-12-31 | 5000 | N | Property/Shed
8 | Finalize building plans with architect or draftsperson | 2025-12-31 | 3000 | N | Planning/Foundation
9 | Level ground for construction pad/house site | 2026-01-31 | 4000 | N | Planning/Foundation
10 | Schedule soil compaction, drainage planning, driveway access for concrete trucks | 2026-01-31 | 3500 | N | Planning/Foundation
12 | Place pier moldings / forms (if pier system) | 2026-02-28 | 3000 | N | Planning/Foundation
13 | Order concrete + pump truck for piers/footings | 2026-03-30 | 5000 | N | Planning/Foundation
14 | Inspection (foundation stage) | 2026-03-30 | 500 | N | Planning/Foundation
15 | Install beams / girders across piers | 2026-04-30 | 8000 | N | Planning/Foundation
16 | Run below-floor utility sleeves / conduit | 2026-04-30 | 2000 | N | Planning/Foundation
17 | Install subflooring / floor deck | 2026-05-30 | 7000 | N | Planning/Foundation
18 | Frame walls (studs, plates, headers) | 2026-06-30 | 20000 | N | Framing/Shell
19 | Install roof joists / trusses | 2026-07-30 | 12000 | N | Framing/Shell
20 | Install roof decking / planks | 2026-07-30 | 7000 | N | Framing/Shell
21 | Sheath walls & roof (plywood/OSB) | 2026-08-30 | 8000 | N | Framing/Shell
22 | Apply housewrap & roofing underlayment | 2026-08-31 | 2000 | N | Framing/Shell
23 | Set windows & exterior doors | 2026-08-31 | 15000 | N | Framing/Shell
24 | Dry-in roof (metal/shingles) | 2026-08-31 | 12000 | N | Framing/Shell
25 | Rough plumbing (supply, drain/vent) | 2026-09-01 | 10000 | N | Rough-ins
26 | Rough electrical (boxes, circuits, panel tie-in) | 2026-09-02 | 10000 | N | Rough-ins
27 | Rough HVAC (ducts or mini-split runs) | 2026-09-03 | 8000 | N | Rough-ins
28 | Inspection (framing + MEP rough) | 2026-09-04 | 500 | N | Rough-ins
29 | Insulation (walls, ceiling, floor if crawlspace) | 2026-09-05 | 6000 | N | Close-in
30 | Drywall (hang, tape, finish) | 2026-09-06 | 10000 | N | Close-in
31 | Exterior siding & trim, caulking, paint | 2026-09-07 | 12000 | N | Close-in
32 | Install interior doors, trim, cabinets | 2026-09-08 | 15000 | N | Finishes
33 | Flooring (tile, LVP, carpet) | 2026-09-09 | 10000 | N | Finishes
34 | Final plumbing fixtures & water heater | 2026-09-10 | 6000 | N | Finishes
35 | Final electrical fixtures, devices, breakers | 2026-09-11 | 6000 | N | Finishes
36 | HVAC install / test | 2026-09-12 | 5000 | N | Finishes
37 | Painting & touch-ups | 2026-09-13 | 4000 | N | Finishes
38 | Final inspection & certificate of occupancy | 2026-09-14 | 500 | N | Finalization
39 | Grade lot for drainage, install gutters/downspouts | 2026-09-15 | 5000 | N | Finalization
40 | Seed, gravel, or fence for site finishing | 2026-09-16 | 3000 | N | Finalization
41 | Move into house & convert shed into other use | 2026-09-17 | 2000 | N | Finalization
|  | Estimated cost | 243700
|  | Contigency | 24370
|  | Budgeted cost: | 268070